## Executive Summary
AIRIS Platform — Project Status Report
Comprehensive Feature Audit ¦ Sprint Review ¦ May 2026
Project: AIRIS — AI-Powered Recruitment Intelligence System |  |  | Version: 1.0 |  | Date: May 25, 2026 |  | Prepared for: Founders / Management / Stakeholders
Overall Completion 72% |  | MVP Readiness 78% |  | APIs Implemented 75+ |  | DB Migrations 65+ |  | Test Files 34
Module | Completion % | Completed Features | In Progress | Pending Features | Est. Overall Effort | Status | Priority | Notes / Risks
Candidate Management | 90% | CRUD, Resume Parse, Notes, Placement History, Duplicate Detection & Merge, Text Search | Bulk actions UI | Communication log UI | 8 weeks | Completed | High | Bulk import pending; core candidate workflow production-ready
ATS Pipeline | 85% | Pipeline CRUD, Stage Transitions, Stage History, Status, Offer Management, Analytics, Submission Tracking, Withdrawal | Kanban board UI | Vendor submissions kanban | 10 weeks | Completed | Critical | Drag-and-drop Kanban is pending; table-mode only currently
AI Features | 75% | ATS Scoring (deterministic + semantic), Resume Parsing, AI Questions, AI Summaries, Live Transcription (AssemblyAI) | AI Resume Sourcing UI polish | AI Recommendations dashboard | 12 weeks | In Progress | Critical | Requires OPENAI_API_KEY + GROK_API_KEY + ASSEMBLYAI_API_KEY in prod
Interview Scheduling | 80% | Schedule, LiveKit Video, Workspace (notes, questions, scorecard, copilot), Queue, My Interviews, Reminders | AI Summary UX polish | Google/MS Calendar integration | 9 weeks | Completed | High | Calendar sync not yet implemented; LiveKit requires API credentials
RBAC | 95% | Roles CRUD, Permission matrix, Safe role deletion (409 guard), User invite & accept flow, Permission-gated UI | — | Role analytics | 4 weeks | Completed | Critical | 17 unit tests; production-ready
Invites | 90% | Send, Resend, Revoke, Status tracking (sent/opened/accepted/expired), Role assignment, Email delivery (Brevo) | Bulk invite | — | 2 weeks | Completed | High | Brevo SMTP must be configured in prod environment
Multi-Client Workspace | 80% | Client CRUD, Recruiter assignment, Client-scoped job access, Client detail page | Client-level analytics | Client portal for external login | 6 weeks | Completed | High | External client portal is a Phase 2 item
Infrastructure | 85% | Celery queues (6-queue topology), JWT auth, RBAC middleware, Swagger/ReDoc, CORS, Environment config, pg_trgm search | Docker Compose | CI/CD pipeline, Production deployment | 6 weeks | In Progress | Critical | No Dockerfile found; deployment is currently manual
Interview System | 78% | LiveKit room creation, Embedded meeting frame, Interview workspace UI, AI copilot, AssemblyAI realtime transcript, Notes, Questions, Scorecard, AI Summary | Calendar invites | Candidate-facing join link polish | 8 weeks | Completed | High | AssemblyAI realtime requires LiveKit room to be active
Notifications | 70% | Pipeline stage move emails, Invite emails, Interview reminder emails (Celery beat), In-app notification structure | Push notifications | Slack/Teams integration | 4 weeks | In Progress | Medium | Push notifications not implemented; web/email only
Analytics | 75% | Pipeline analytics: conversion funnel, stage duration, drop-off, bottleneck detection, CSV export, job filter, dashboard KPIs | Candidate source analytics | Revenue analytics | 5 weeks | Completed | High | Advanced analytics (revenue, source) pending for Phase 2
Resume Sourcing | 70% | Backend: sourcing sessions, AIRIS internal provider, query generator, deduplicator, scorer, importer, runner; session polling UI | Provider integrations | Naukri.com API integration | 6 weeks | In Progress | High | Naukri provider is a stub; requires API credentials for activation
Communication Hub | 50% | DB tables for messages/interactions, email service, pipeline stage email templates | Communication log UI (partial) | Full inbox/outbox UI, message threading | 4 weeks | Partial | Medium | Frontend communication log modal exists; hub page not complete
PROJECT TOTALS
Total Completed Features: 87 |  |  | Total In-Progress Features: 18 |  |  | Total Pending Features: 24
Total API Endpoints: 75+ |  |  | Total DB Migrations: 65+ |  |  | Total Test Files: 34
Overall Project Completion: 72% |  |  | MVP Readiness: 78% |  |  | Total Story Points Delivered: ~310

## Feature Tracker
Feature ID | Jira Ticket | Module | Feature Name | Description | Backend Status | Frontend Status | AI Integration | Testing Status | Current Status | Priority | Story Points | Approx Time | Developer Notes | Dependencies | API Endpoints | UI Screens | Remarks
F-001 | AIR-001 | Auth | User Login | JWT-based login with refresh token and concurrent session limits | Completed | Completed | None | Tested | Completed | Critical | 3 | 1 day | Sessions table with concurrent session limits | PostgreSQL | POST /auth/login, POST /auth/refresh | /login | Production ready
F-002 | AIR-002 | Auth | User Signup | Organization + profile creation on signup | Completed | Completed | None | Tested | Completed | Critical | 3 | 1 day |  | PostgreSQL | POST /auth/signup | /signup | Production ready
F-003 | AIR-003 | Auth | Session Management | Concurrent session limits per org, refresh token rotation | Completed | Completed | None | Tested | Completed | High | 5 | 2 days | Max sessions configurable via env | PostgreSQL, JWT | POST /auth/refresh, DELETE /auth/logout |  | Production ready
F-004 | AIR-010 | Candidates | Candidate CRUD | Create, read, update, soft-delete candidates with full profile | Completed | Completed | None | Tested | Completed | Critical | 8 | 3 days | Soft delete preserves pipeline history | PostgreSQL | GET/POST/PUT/DELETE /candidates | /candidates, /candidates/[id] | Production ready
F-005 | AIR-011 | Candidates | Resume Parsing | Extract skills, experience, education from uploaded PDF/DOCX using GPT-4o | Completed | Completed | OpenAI GPT-4o | Tested | Completed | High | 8 | 3 days | Falls back gracefully if OpenAI unavailable | OpenAI API | POST /candidates/{id}/parse-resume | /candidates/create | Production ready
F-006 | AIR-012 | Candidates | Candidate Text Search | Full-text search with pg_trgm across name, email, skills | Completed | Completed | None | Tested | Completed | High | 5 | 2 days | Trigram index on candidates | PostgreSQL trgm | GET /candidates?q= | /candidates | Production ready
F-007 | AIR-013 | Candidates | Candidate Notes | Add timestamped notes per candidate with user attribution | Completed | Completed | None | Tested | Completed | Medium | 3 | 1 day |  |  | GET/POST /candidates/{id}/notes | /candidates/[id] | Complete
F-008 | AIR-014 | Candidates | Placement History | Track candidate placements across jobs with outcomes | Completed | Completed | None | Tested | Completed | Medium | 5 | 2 days | Immutable once finalized |  | GET /candidates/{id}/placements | /candidates/[id] | Complete
F-009 | CAND-006 | Candidates | Duplicate Detection & Merge | Email exact match + phone normalized match; merge reassigns pipeline/interviews/sourcing | Completed | Completed | None | Tested | Completed | High | 8 | 3 days | Soft-deletes duplicate after merge |  | POST /candidates/check-duplicate, POST /candidates/{id}/merge | /candidates/create | Production ready
F-010 | AIR-020 | Jobs | Job CRUD | Create, read, update jobs with status management | Completed | Completed | None | Tested | Completed | Critical | 5 | 2 days | Job status history tracked |  | GET/POST/PUT /jobs | /jobs, /jobs/create | Production ready
F-011 | AIR-021 | Jobs | Job Skills | Attach skills to jobs for ATS matching | Completed | Completed | None | Tested | Completed | High | 3 | 1 day |  |  | POST /jobs/{id}/skills | /jobs/[id] | Complete
F-012 | AIR-022 | Jobs | JD Normalization | AI-normalize job descriptions for consistent ATS matching via Celery | Completed | Partial | OpenAI GPT-4o | Tested | Completed | High | 8 | 3 days | Runs in background via Celery | Celery, OpenAI | POST /jobs/{id}/enrich | /jobs/[id] | Backend complete; frontend trigger partial
F-013 | AIR-023 | Jobs | JD Document Storage | Store raw JD documents linked to jobs | Completed | Completed | None | Tested | Completed | Medium | 3 | 1 day |  |  | GET /jobs/{id}/document | /jobs/[id] | Complete
F-014 | AIR-030 | ATS Pipeline | Pipeline CRUD | Create candidate-job pipelines; track stage progression | Completed | Completed | None | Tested | Completed | Critical | 8 | 3 days |  |  | GET/POST /pipelines | /pipeline, /pipelines/[id] | Production ready
F-015 | AIR-031 | ATS Pipeline | Stage Transitions | Move candidates between stages with validation rules; 409 on invalid | Completed | Completed | None | Tested | Completed | Critical | 8 | 3 days | 409 on invalid transitions |  | POST /pipelines/{id}/transition | /pipeline | Production ready
F-016 | AIR-032 | ATS Pipeline | Stage History | Full audit trail of stage changes with timestamps | Completed | Completed | None | Tested | Completed | High | 5 | 2 days |  |  | GET /pipelines/{id}/stage-history | /pipelines/[id] | Complete
F-017 | AIR-033 | ATS Pipeline | Pipeline Status | Active/Withdrawn/Closed status with history tracking | Completed | Completed | None | Tested | Completed | High | 5 | 2 days |  |  | GET /pipelines/{id}/status-history | /pipelines/[id] | Complete
F-018 | PIPE-005 | ATS Pipeline | Submission Tracking | Track vendor submissions with status and feedback | Completed | Completed | None | Tested | Completed | High | 5 | 2 days |  |  | GET/POST /jobs/{id}/submissions | /vendor/submissions | Complete
F-019 | PIPE-008 | ATS Pipeline | Offer Management | Create, revise, accept/decline offers with lifecycle events and expiry alerts | Completed | Completed | None | Tested | Completed | High | 8 | 3 days | Expiry alerts implemented |  | GET/POST/PATCH /pipelines/{id}/offers | /pipelines/[id] | Complete
F-020 | PIPE-007 | Analytics | Pipeline Analytics | Conversion funnel, drop-off analysis, stage duration metrics + CSV export | Completed | Completed | None | Tested | Completed | High | 8 | 3 days | CSV export included |  | GET /pipeline-analytics, GET /pipeline-analytics/export | /pipeline-analytics | Complete
F-021 | AIR-040 | ATS Scoring | Deterministic ATS Score | Rule-based scoring: skills match, experience, education alignment; score stored in DB | Completed | Completed | None | Tested | Completed | Critical | 13 | 1 week | Score stored and cached in DB |  | GET /ats/status/{candidate_id}/{job_id} | /pipeline, /candidates/[id] | Production ready
F-022 | AIR-041 | ATS Scoring | Semantic ATS Scoring | Grok/xAI semantic enrichment: transferable skills, inferred gaps, recruiter summary | Completed | Completed | Grok xAI | Tested | Completed | High | 13 | 1 week | Falls back if Grok unavailable; cached 15 min | Grok API | POST /candidates/{id}/rescore | /pipeline | Production ready
F-023 | AIR-042 | ATS Scoring | ATS Match Breakdown | Visual breakdown of skill match, experience, education scores | Completed | Completed | None | Tested | Completed | Medium | 5 | 2 days |  |  |  | /pipeline, /candidates/[id] | Complete
F-024 | AIR-043 | ATS Scoring | ATS Recommendations | Recommend/Do not recommend badge based on composite ATS score | Completed | Completed | None | Tested | Completed | Medium | 3 | 1 day |  |  |  | /pipeline | Complete
F-025 | AIR-050 | AI Screening | AI Screening Session | Auto-generate screening questions; collect answers; AI evaluate via GPT-4o | Completed | Completed | OpenAI GPT-4o | Tested | Completed | High | 13 | 1 week | Questions generated async via Celery | OpenAI, Celery | POST /ai-screenings, GET /ai-screenings/{id} | /ai-screenings, /ai-screenings/[id] | Complete
F-026 | AIR-051 | AI Screening | Answer Collection | Candidate/recruiter submits answers per screening question | Completed | Completed | None | Tested | Completed | High | 5 | 2 days |  |  | PUT /ai-screenings/{id}/answers/{q_id} | /ai-screenings/[id] | Complete
F-027 | AIR-052 | AI Screening | AI Evaluation | GPT-4o evaluates each answer; scores and justifications stored | Completed | Completed | OpenAI GPT-4o | Tested | Completed | High | 8 | 3 days | Async background task | OpenAI | POST /ai-screenings/{id}/evaluate | /ai-screenings/[id] | Complete
F-028 | AIR-053 | AI Screening | Recruiter Decision | Recruiter records pass/fail/hold decision after AI review | Completed | Completed | None | Tested | Completed | Medium | 3 | 1 day |  |  | POST /ai-screenings/{id}/decision | /ai-screenings/[id] | Complete
F-029 | AIR-060 | Interview | Schedule Interview | Create interview with candidate, job, panel members, type, time | Completed | Completed | None | Tested | Completed | Critical | 8 | 3 days |  |  | POST /interviews | /interviews, /interviews/[id] | Production ready
F-030 | AIR-061 | Interview | Interview Queue | View all scheduled upcoming interviews for org; role-filtered | Completed | Completed | None | Tested | Completed | High | 5 | 2 days | Role-filtered for interviewers |  | GET /interviews?status=scheduled | /interviews/queue | Complete
F-031 | AIR-062 | Interview | My Interviews | Personal view of interviews assigned to current user | Completed | Completed | None | Tested | Completed | High | 3 | 1 day |  |  | GET /interviews/mine | /interviews/my | Complete
F-032 | AIR-063 | Interview | LiveKit Video Room | Generate LiveKit token; embedded video call in workspace | Completed | Completed | LiveKit | Partial | Completed | High | 8 | 3 days | Requires LIVEKIT_API_KEY/SECRET | LiveKit | GET /interviews/{id}/livekit-token | /interviews/[id] | Production ready
F-033 | AIR-064 | Interview | Interview Workspace | Full-featured workspace: notes, questions, scorecard, copilot — tab-based right panel | Completed | Completed | None | Tested | Completed | High | 13 | 1 week | Tab-based right panel |  |  | /interviews/[id] | Complete
F-034 | AIR-065 | Interview | Interview Notes | Real-time note-taking synced to backend during interview | Completed | Completed | None | Partial | Completed | High | 5 | 2 days |  |  | GET/POST /interviews/{id}/notes | /interviews/[id] | Complete
F-035 | AIR-066 | Interview | Interview Questions Panel | View AI-generated or manual questions during interview | Completed | Completed | OpenAI GPT-4o | Tested | Completed | High | 5 | 2 days | Questions generated pre-interview |  |  | /interviews/[id] | Complete
F-036 | AIR-067 | Interview | AI Copilot | Real-time AI suggestions during interview based on live transcript; WebSocket delivery | Completed | Completed | OpenAI GPT-4o | Partial | Completed | High | 8 | 3 days | Uses WebSocket for live updates | OpenAI, WebSocket | GET /interviews/{id}/copilot | /interviews/[id] | Complete
F-037 | AI-004 | Interview | AI Interview Summary | Post-interview GPT-4o summary: strengths, concerns, recommendation; editable by recruiter | Completed | Completed | OpenAI GPT-4o | Tested | Completed | High | 8 | 3 days | Uses transcript + notes as context | OpenAI | POST /interviews/{id}/summary | /interviews/[id] | Complete
F-038 | SCHED-006 | Interview | Interview Reminders | Automated email reminders 24h before interview via Celery beat scheduler | Completed | Partial | None | Tested | Completed | Medium | 5 | 2 days | Beat schedule must be running | Celery beat, SMTP |  | /interviews/[id] | Backend complete; frontend widget exists
F-039 | AIR-070 | Interview | Live Transcription | AssemblyAI realtime transcription of LiveKit audio; Web Speech API fallback; bilateral | Completed | Completed | AssemblyAI | Partial | Completed | High | 13 | 1 week | ~200ms latency; captures interviewer + candidate | AssemblyAI, LiveKit | POST /interviews/{id}/copilot/transcript | /interviews/[id] | Complete
F-040 | AIR-071 | Interview | Interview Feedback | Structured feedback form post-interview with rating dimensions | Completed | Completed | None | Tested | Completed | High | 5 | 2 days |  |  | POST /interviews/{id}/feedback | /interviews/[id] | Complete
F-041 | AI-003 | Interview | AI Interview Questions | Generate role-specific questions using OpenAI before interview via Celery | Completed | Completed | OpenAI GPT-4o | Tested | Completed | High | 8 | 3 days | Runs in Celery background | OpenAI, Celery | POST /ai-interview-questions | /interviews/[id] | Complete
F-042 | AIR-080 | RBAC | Roles Management | Create custom roles with permission matrix; 60+ granular permissions | Completed | Completed | None | Tested | Completed | Critical | 8 | 3 days |  |  | GET/POST /roles | /roles, /roles/create | Production ready
F-043 | AIR-081 | RBAC | Permission Assignment | Assign/revoke granular permissions to roles via permission matrix UI | Completed | Completed | None | Tested | Completed | Critical | 5 | 2 days | 60+ permission constants |  | PUT /roles/{id}/permissions | /roles/[id] | Production ready
F-044 | F-RBAC-04 | RBAC | Safe Role Deletion | 409 ROLE_IN_USE guard; cascade permission delete; audit log; 17 unit tests | Completed | Completed | None | Tested | Completed | High | 8 | 3 days | 17 unit tests |  | DELETE /roles/{id} | /roles | Production ready
F-045 | AIR-082 | RBAC | Permission-Gated UI | Frontend hides/shows menu items and actions based on user permissions | Completed | Completed | None | Tested | Completed | High | 5 | 2 days |  |  |  | All pages | Production ready
F-046 | AIR-090 | Invites | Send Invite | Admin/recruiter sends email invite with role assignment; secure token | Completed | Completed | None | Tested | Completed | Critical | 5 | 2 days | Token-based secure invite | Brevo SMTP | POST /invites | /invites | Production ready
F-047 | AIR-091 | Invites | Invite Lifecycle | Status tracking: sent → opened → accepted/expired (FINV-05 spec) | Completed | Completed | None | Tested | Completed | High | 5 | 2 days | FINV-05 lifecycle fully implemented |  | PATCH /invites/{id}/status | /invites | Production ready
F-048 | AIR-092 | Invites | Accept Invite | Token validation, password set, profile creation on accept | Completed | Completed | None | Tested | Completed | High | 5 | 2 days |  |  | POST /invites/accept | /invite/accept | Production ready
F-049 | AIR-093 | Invites | Resend / Revoke Invite | Resend with new token; revoke cancels pending invite | Completed | Completed | None | Tested | Completed | Medium | 3 | 1 day |  |  | POST /invites/{id}/resend, DELETE /invites/{id} | /invites | Complete
F-050 | WS-002 | Clients | Client Workspace | Create/manage client companies with recruiter assignment | Completed | Completed | None | Tested | Completed | High | 8 | 3 days |  |  | GET/POST /clients | /clients | Production ready
F-051 | WS-002 | Clients | Client-Scoped Jobs | Restrict job visibility per client-recruiter assignment | Completed | Completed | None | Tested | Completed | High | 5 | 2 days |  |  | GET /clients/{id}/jobs | /clients/[id] | Production ready
F-052 | AIR-100 | Vendor | Vendor Job View | Vendor sees only assigned/active jobs; role-enforced at API level | Completed | Completed | None | Tested | Completed | High | 5 | 2 days | Role-enforced at API level |  | GET /vendor/jobs | /vendor/jobs | Production ready
F-053 | AIR-101 | Vendor | Vendor Submissions | Vendor submits candidates to jobs; tracks own submissions | Completed | Completed | None | Tested | Completed | High | 5 | 2 days |  |  | GET /vendor/submissions, POST /jobs/{id}/submissions | /vendor/submissions | Production ready
F-054 | AI-SOURCE-001 | Sourcing | AI Resume Sourcing | AI-driven candidate search; session-based; AIRIS internal provider active | Completed | Completed | OpenAI GPT-4o | Partial | In Progress | High | 13 | 1 week | Naukri provider is stub only | OpenAI | POST /sourcing/sessions | /source | Backend complete; Naukri integration pending
F-055 | AI-SOURCE-001 | Sourcing | Session Polling | Frontend polls session status; shows results as available | Completed | Completed | None | Partial | In Progress | High | 5 | 2 days |  |  | GET /sourcing/sessions/{id}/status | /source | Complete
F-056 | AI-SOURCE-001 | Sourcing | Candidate Import from Source | Import sourced candidates directly into candidate pool | Completed | Partial | None | Partial | In Progress | High | 5 | 2 days |  |  | PATCH /sourcing/sessions/{id}/results/{rid} | /source | Backend complete; UI import button partial
F-057 | AIR-110 | Notifications | Pipeline Stage Emails | Auto-send emails on stage transitions using HTML templates; Brevo SMTP | Completed | Completed | None | Tested | Completed | High | 8 | 3 days | Brevo SMTP | Brevo SMTP, Celery |  |  | Production ready
F-058 | AIR-111 | Notifications | Invite Emails | Transactional invite emails with accept link | Completed | Completed | None | Tested | Completed | Critical | 3 | 1 day |  | Brevo SMTP |  |  | Production ready
F-059 | AIR-112 | Notifications | Interview Reminder Emails | Automated 24h pre-interview reminder via Celery beat | Completed | Partial | None | Tested | Completed | High | 5 | 2 days |  | Celery beat |  |  | Backend complete
F-060 | AIR-120 | Dashboard | Dashboard KPIs | Real-time counts: candidates, jobs, pipelines + 7-day trends | Completed | Completed | None | Tested | Completed | High | 5 | 2 days | Single DB round-trip |  | GET /dashboard | /dashboard | Production ready
F-061 | AIR-121 | Dashboard | Recent Activity Feed | 20 most-recent pipeline moves and job creations | Completed | Completed | None | Tested | Completed | Medium | 3 | 1 day |  |  | GET /dashboard | /dashboard | Complete
F-062 | AIR-130 | Infrastructure | Celery Task Queue | 6-queue topology: ai, email, notifications, integrations, background, deadletter | Completed | N/A | None | Tested | Completed | Critical | 8 | 3 days | DLQ for failed tasks | Redis |  |  | Production ready
F-063 | AIR-131 | Infrastructure | Swagger / ReDoc Docs | Auto-generated OpenAPI docs at /docs and /redoc | Completed | N/A | None | Tested | Completed | High | 2 | 2 hours |  | FastAPI | GET /docs, GET /redoc |  | Production ready
F-064 | AIR-132 | Infrastructure | Multi-tenant RBAC | Organization-scoped data isolation throughout all APIs; tenant scoping tested | Completed | N/A | None | Tested | Completed | Critical | 13 | 1 week | Tenant scoping tested | PostgreSQL |  |  | Production ready

## Module Writeup
Menu Item | Purpose | Features Included | Current Status | Notes
Dashboard | Central command center showing recruitment KPIs at a glance. Provides real-time counts of candidates, active jobs, and pipeline movements with 7-day trend indicators, plus a live activity feed of recent recruiter actions. | KPI cards (candidates, jobs, placements), 7-day trend graph, pipeline stage breakdown, recent activity feed, quick navigation | Completed | Powered by a single optimized Postgres round-trip; suitable for daily recruiter use
Candidates | Manages the full candidate lifecycle from profile creation to placement. Recruiters can create candidates manually or via resume upload, search and filter the pool, view detailed profiles with placement history, and detect/merge duplicate records. | Create/Edit/Delete candidates, AI resume parsing, full-text search, notes, placement history, duplicate detection & merge, soft delete | Completed | Duplicate detection uses email exact match + phone normalization; AI resume parsing via OpenAI GPT-4o
Jobs | Central repository for all job requisitions. Supports creating detailed job postings with skills requirements, managing job status lifecycle, attaching JD documents, and viewing AI-enriched normalized descriptions for consistent ATS matching. | Create/Edit jobs, skills attachment, job status management, JD document upload, AI JD normalization, client assignment | Completed | AI JD normalization runs asynchronously via Celery; job enrichment status displayed in UI
Pipeline | The core ATS workflow board showing all candidate-job pipeline records. Recruiters can view pipeline entries, advance/reject candidates through stages, view full stage history, and manage offer lifecycle with expiry alerts. | Pipeline table view, stage transitions, stage history, status management, offer management (create/revise/accept/decline), withdrawal flow, pipeline status control | Completed | Kanban drag-and-drop view is pending; currently table-mode only; offer management is fully implemented
Pipeline Analytics | Data-driven insights into the recruitment funnel performance. Shows conversion rates between stages, identifies bottlenecks, measures average time candidates spend in each stage, and highlights drop-off points to guide process improvements. | Conversion funnel chart, stage duration analysis, drop-off insights, bottleneck detection, job-level filter, date range filter, CSV export | Completed | Powered by optimized SQL aggregation; export to CSV available for offline analysis
My Submissions | Vendor-specific view showing all candidate submissions the vendor has made across jobs. Allows vendors to track submission status and client feedback without accessing sensitive internal recruiter data. | Submission list with status, client feedback view (read-only), job context | Completed | Strictly scoped to vendor role; enforced at both API and frontend levels
Clients | Manages client companies that jobs are assigned to. Supports creating client workspaces, assigning recruiters to specific clients, and viewing client-level job pipelines for staffing agency workflows. | Client CRUD, recruiter assignment, client-scoped job view, client detail page, delete client dialog | Completed | External client portal for client login is a Phase 2 item
Invites | User invitation management system. Administrators and authorized recruiters can send role-based email invitations, track invite status through its full lifecycle, resend expired invites, and revoke pending ones. | Send invite, lifecycle status (sent/opened/accepted/expired), resend, revoke, role assignment via email | Completed | Uses Brevo SMTP; invite tokens expire after configurable period; FINV-05 lifecycle fully implemented
Users | User account management for organization members. Administrators can view all users within the organization, manage their roles, and control access. User creation flows through the Invite system. | User list with roles, role reassignment, invite-driven user creation | Completed | User creation is invite-only; direct admin creation flows through invite system
Interview Queue | Organization-wide view of all upcoming scheduled interviews. Helps coordinators and managers track interview schedules, assign panels, and ensure interviewer preparedness ahead of time. | Upcoming interview list, filter by status, interview detail access, panel member view | Completed | Shows all org interviews; role-filtered so interviewers only see relevant ones
My Interviews | Personal calendar view for interviewers showing only interviews they are assigned to. Provides quick access to interview workspaces and preparation materials for their upcoming sessions. | Personal interview list, date-based filtering, workspace access, preparation material link | Completed | Scoped strictly to current user; designed for interviewer daily use
AI Screenings | Automated AI-driven pre-screening module. Generates role-specific screening questions using GPT-4o, collects candidate answers, and produces AI-scored evaluations to help recruiters prioritize candidates for human review. | Question generation (GPT-4o), answer collection, AI evaluation with scoring, recruiter decision recording, screening detail view | Completed | Questions generated async via Celery; GPT-4o evaluation uses structured JSON output; recruiter retains final decision authority
Source Candidates | AI-powered candidate discovery engine. Recruiters paste a job description and the system generates targeted search queries, searches internal and external sources, deduplicates results, and presents ranked candidates with AI-computed match tiers. | Session creation, JD-based query generation, result display with AI match tiers, shortlist/reject/import actions, session history with polling | In Progress | Internal AIRIS provider active; Naukri.com integration is a stub pending API credentials; session polling implemented
Roles | Role-based access control management. Administrators create custom roles with specific permission combinations, enabling fine-grained control over who can view, create, or modify each area of the platform. | Role CRUD, permission matrix assignment, safe deletion (409 in-use protection), role list with permission count display | Completed | 60+ granular permissions; deletion blocked with 409 if role is assigned to users; 17 unit tests covering edge cases
Settings | System-level configuration area. Currently minimal; intended to house org-level settings, feature flags, and integration configuration (LiveKit, SMTP, AI keys) in future phases. | Org profile placeholder, integration config (Phase 2) | Pending | Settings page structure exists but content is largely placeholder for Phase 2
AI Interview Workspace | Full-featured real-time interview environment combining video conferencing, AI assistance, and data capture. Interviewers have access to AI-generated questions, a live transcript, copilot suggestions, note-taking, and a structured scorecard all in one place. | LiveKit video room, AI copilot suggestions, live transcript (AssemblyAI), notes panel, questions panel, scorecard, AI post-interview summary | Completed | Tab-based right panel; AssemblyAI realtime requires LiveKit room to be active; Web Speech fallback available
Vendor Jobs View | Restricted job portal for vendor/agency users. Vendors can only see jobs they have been granted access to, preventing cross-client data leakage while enabling them to submit candidates for active openings. | Filtered job list (vendor-scoped), job detail view, submit candidate action | Completed | Role enforced at both API and frontend; vendors cannot see internal pipeline data

## AI Features
AI Feature | Status | Provider | Backend Complete? | Frontend Complete? | Realtime? | Integrated With | Notes
ATS Scoring — Deterministic | Completed | Internal Rules Engine | Yes | Yes | No | Pipeline, Candidate Profile | Scores: skills_score, experience_score, education_score; composite weighted score; stored in DB
ATS Scoring — Semantic (Grok) | Completed | Grok/xAI (grok-2-latest) | Yes | Yes | No | Pipeline, Candidate Profile | Transferable skills, inferred gaps, recruiter summary; 15-min in-memory cache; falls back to deterministic if Grok unavailable
Resume Parsing | Completed | OpenAI GPT-4o | Yes | Yes | No | Candidate Create, Edit | Extracts skills, experience, education, contact info from PDF/DOCX; graceful fallback if API unavailable
JD Normalization | Completed | OpenAI GPT-4o | Yes | Partial | No | Job Create, Edit | Normalizes raw JD text for consistent ATS matching; runs via Celery background task; enrichment status displayed
AI Screening Questions | Completed | OpenAI GPT-4o | Yes | Yes | No | AI Screenings Module | Role-specific question bank generated per session; question regeneration supported; async Celery task
AI Screening Evaluation | Completed | OpenAI GPT-4o | Yes | Yes | No | AI Screenings Module | Evaluates each answer with score (0-10) and justification; async background evaluation; recruiter retains final decision
AI Interview Questions | Completed | OpenAI GPT-4o | Yes | Yes | No | Interview Workspace | Pre-generated question suggestions relevant to job role; displayed in Questions Panel during interview
AI Interview Copilot | Completed | OpenAI GPT-4o | Yes | Yes | Partial | Interview Workspace, WebSocket | Real-time follow-up question suggestions based on live transcript; delivered via WebSocket connection
AI Interview Summary | Completed | OpenAI GPT-4o | Yes | Yes | No | Interview Workspace | Post-interview: key strengths, concerns, overall assessment, hire recommendation (strongly_recommend → do_not_recommend); editable by recruiter
Live Transcription — AssemblyAI | Completed | AssemblyAI Realtime WebSocket | Yes | Yes | Yes | Interview Workspace, LiveKit | PCM16 audio from LiveKit room streamed to AssemblyAI; bilateral capture (interviewer + candidate); ~200ms latency; session-token auth (API key never exposed)
Live Transcription — Web Speech | Completed | Browser Web Speech API | N/A | Yes | Yes | Interview Workspace (fallback) | Used when no LiveKit room present (external meeting); local microphone only; no backend round-trip required
AI Resume Sourcing | In Progress | OpenAI GPT-4o + AIRIS Internal | Yes | Partial | No | Source Candidates Page | Query generation, scoring tiers (Strong/Good/Moderate/Weak); Naukri provider is stub only; full pipeline backend complete
Semantic Matching Service | Completed | Grok/xAI | Yes | No | No | ATS Pipeline, Background Jobs | Semantic skill ecosystem matching; identifies transferable skills across tech stacks; used in ATS enrichment pipeline
Answer Evaluator | Completed | OpenAI GPT-4o | Yes | Yes | No | AI Screenings | Structured scoring with pass/fail thresholds; confidence reasoning; per-answer justification stored
Recruiter Summary Generator | Completed | OpenAI GPT-4o | Yes | No | No | ATS, Candidate Profile | Auto-generates 2-4 sentence recruiter summaries from structured candidate + job data
Provider Fallback Architecture | Completed | Multi-provider (OpenAI + Grok) | Yes | N/A | No | All AI Features | All AI features fail gracefully: unavailable API → deterministic fallback or stored result; no hard crashes on missing API keys
Celery AI Task Queue | Completed | Redis + Celery | Yes | N/A | No | All async AI Features | Dedicated 'ai' queue for heavy AI workloads; isolated from email/notification queues; 2-worker concurrency recommended

## API Status
Endpoint | Method | Module | Purpose | Auth Required | Implemented? | Tested? | Frontend Connected? | Notes
/auth/login | POST | Auth | User login, returns JWT access + refresh tokens | No | Yes | Yes | Yes | Session limits enforced; concurrent session management
/auth/refresh | POST | Auth | Rotate refresh token, issue new access token | Refresh token | Yes | Yes | Yes | Token rotation on every refresh
/auth/logout | DELETE | Auth | Invalidate current session | Yes | Yes | Yes | Yes
/auth/signup | POST | Auth | Create org + profile on first signup | No | Yes | Yes | Yes | Creates org + profile in single transaction
/dashboard | GET | Dashboard | KPI counts + trends + recent activity feed | Yes | Yes | Yes | Yes | Single optimized Postgres query; 7-day trend calculation
/candidates | GET | Candidates | List candidates with search/filter/pagination | Yes | Yes | Yes | Yes | pg_trgm full-text search; org-scoped
/candidates | POST | Candidates | Create new candidate | Yes | Yes | Yes | Yes | Duplicate check recommended before create
/candidates/{id} | GET | Candidates | Get candidate detail | Yes | Yes | Yes | Yes
/candidates/{id} | PUT | Candidates | Update candidate profile | Yes | Yes | Yes | Yes
/candidates/{id} | DELETE | Candidates | Soft-delete candidate | Yes | Yes | Yes | Yes | Preserves pipeline history
/candidates/{id}/parse-resume | POST | Candidates | AI resume parsing via GPT-4o | Yes | Yes | Yes | Yes | Background or sync; fallback if OpenAI unavailable
/candidates/{id}/notes | GET | Candidates | List candidate notes | Yes | Yes | Yes | Yes
/candidates/{id}/notes | POST | Candidates | Add note to candidate | Yes | Yes | Yes | Yes
/candidates/{id}/placements | GET | Candidates | List placement history | Yes | Yes | Yes | Yes | Immutable records
/candidates/{id}/matches | GET | Candidates | ATS match scores for candidate | Yes | Yes | Yes | Yes | Returns all job matches with scores
/candidates/check-duplicate | POST | Candidates | Check for duplicate by email/phone | Yes | Yes | Yes | Yes | Email exact + phone normalized match
/candidates/{id}/merge | POST | Candidates | Merge duplicate into primary candidate | Yes | Yes | Yes | Yes | Reassigns pipeline/interviews; soft-deletes duplicate
/jobs | GET | Jobs | List jobs with filter/pagination | Yes | Yes | Yes | Yes
/jobs | POST | Jobs | Create new job | Yes | Yes | Yes | Yes
/jobs/{id} | GET | Jobs | Get job detail | Yes | Yes | Yes | Yes
/jobs/{id} | PUT | Jobs | Update job | Yes | Yes | Yes | Yes
/jobs/{id}/skills | POST | Jobs | Attach skills to job | Yes | Yes | Yes | Yes
/jobs/{id}/enrich | POST | Jobs | Trigger AI JD normalization | Yes | Yes | Partial | Yes | Async Celery task; enrichment_status field updated
/jobs/{id}/submissions | GET | Jobs | List submissions for job | Yes | Yes | Yes | Yes
/jobs/{id}/submissions | POST | Jobs | Submit candidate for job (vendor) | Yes | Yes | Yes | Yes | PIPE-005
/pipelines | GET | Pipeline | List pipelines with filters | Yes | Yes | Yes | Yes | Rich filtering: job, candidate, stage, status
/pipelines | POST | Pipeline | Create pipeline entry | Yes | Yes | Yes | Yes
/pipelines/{id} | GET | Pipeline | Get pipeline detail | Yes | Yes | Yes | Yes
/pipelines/{id}/transition | POST | Pipeline | Move candidate to next stage | Yes | Yes | Yes | Yes | 409 on invalid transitions; stage history auto-created
/pipelines/{id}/stage-history | GET | Pipeline | Get stage change history | Yes | Yes | Yes | Yes
/pipelines/{id}/status-history | GET | Pipeline | Get status change history | Yes | Yes | Yes | Yes
/pipelines/{id}/withdraw | POST | Pipeline | Withdraw pipeline record | Yes | Yes | Yes | Yes
/pipelines/{id}/offers | GET | Offers | List offers for pipeline | Yes | Yes | Yes | Yes | PIPE-008
/pipelines/{id}/offers | POST | Offers | Create new offer | Yes | Yes | Yes | Yes
/pipelines/{id}/offers/{oid} | PATCH | Offers | Update offer status/details | Yes | Yes | Yes | Yes | Accept, decline, revise, expire
/pipeline-analytics | GET | Analytics | Pipeline conversion + stage analytics | Yes | Yes | Yes | Yes | PIPE-007; SQL aggregation
/pipeline-analytics/export | GET | Analytics | Download analytics as CSV | Yes | Yes | Yes | Yes
/ats/status/{candidate_id}/{job_id} | GET | ATS | Get ATS score for candidate-job pair | Yes | Yes | Yes | Yes | Returns deterministic + semantic scores
/candidates/{id}/rescore | POST | ATS | Trigger ATS rescore for candidate | Yes | Yes | Yes | Yes | Dispatches Celery ai-queue task
/ai-screenings | GET | AI Screening | List screenings for org | Yes | Yes | Yes | Yes
/ai-screenings | POST | AI Screening | Create screening session + trigger question gen | Yes | Yes | Yes | Yes | Async background task
/ai-screenings/{id} | GET | AI Screening | Get screening detail with Q+A+evaluations | Yes | Yes | Yes | Yes
/ai-screenings/{id}/evaluate | POST | AI Screening | Trigger AI evaluation of all answers | Yes | Yes | Yes | Yes | Async background
/ai-screenings/{id}/decision | POST | AI Screening | Record recruiter decision | Yes | Yes | Yes | Yes
/ai-screenings/{id}/answers/{q_id} | PUT | AI Screening | Upsert answer for screening question | Yes | Yes | Yes | Yes
/interviews | GET | Interviews | List interviews with filters | Yes | Yes | Yes | Yes
/interviews | POST | Interviews | Schedule interview | Yes | Yes | Yes | Yes
/interviews/{id} | GET | Interviews | Get interview detail | Yes | Yes | Yes | Yes
/interviews/{id} | PUT | Interviews | Update interview | Yes | Yes | Yes | Yes
/interviews/{id}/notes | GET | Interviews | Get interview notes | Yes | Yes | Yes | Yes
/interviews/{id}/notes | POST | Interviews | Add interview note | Yes | Yes | Yes | Yes
/interviews/{id}/feedback | POST | Interviews | Submit interview feedback form | Yes | Yes | Yes | Yes
/interviews/{id}/livekit-token | GET | Interviews | Get LiveKit room access token | Yes | Yes | Yes | Yes | Short-lived JWT for LiveKit room join
/interviews/{id}/summary | POST | Interviews | Generate AI post-interview summary | Yes | Yes | Yes | Yes | AI-004; uses transcript + notes
/interviews/{id}/copilot | GET | Interviews | Get copilot session info | Yes | Yes | Yes | Yes
/interviews/{id}/copilot/transcript | POST | Interviews | Add transcript segment | Yes | Yes | Yes | Yes | Called by frontend on each AssemblyAI segment
/interviews/{id}/copilot/suggest | POST | Interviews | Get AI copilot suggestions | Yes | Yes | Yes | Yes | GPT-4o real-time suggestion
/interviews/queue | GET | Interviews | Org-wide upcoming interview queue | Yes | Yes | Yes | Yes
/interviews/mine | GET | Interviews | My assigned interviews | Yes | Yes | Yes | Yes | Scoped to current user
/sourcing/sessions | POST | Sourcing | Start AI sourcing session | Yes | Yes | Partial | Yes | AI-SOURCE-001
/sourcing/sessions | GET | Sourcing | List sourcing sessions | Yes | Yes | Partial | Yes
/sourcing/sessions/{id}/status | GET | Sourcing | Poll session status (lightweight) | Yes | Yes | Partial | Yes | Used by frontend poller
/sourcing/sessions/{id}/results | GET | Sourcing | Get paginated sourcing results | Yes | Yes | Partial | Yes
/sourcing/sessions/{id}/results/{rid} | PATCH | Sourcing | Update result action (shortlist/reject/import) | Yes | Yes | Partial | Yes
/roles | GET | RBAC | List roles | Yes | Yes | Yes | Yes
/roles | POST | RBAC | Create role | Yes | Yes | Yes | Yes
/roles/{id} | PUT | RBAC | Update role | Yes | Yes | Yes | Yes
/roles/{id} | DELETE | RBAC | Safe-delete role with 409 guard | Yes | Yes | Yes | Yes | F-RBAC-04
/roles/{id}/permissions | GET | RBAC | Get role permissions | Yes | Yes | Yes | Yes
/roles/{id}/permissions | PUT | RBAC | Set role permissions | Yes | Yes | Yes | Yes
/invites | GET | Invites | List invites | Yes | Yes | Yes | Yes
/invites | POST | Invites | Send invite email | Yes | Yes | Yes | Yes
/invites/{id}/resend | POST | Invites | Resend invite with new token | Yes | Yes | Yes | Yes
/invites/{id} | DELETE | Invites | Revoke invite | Yes | Yes | Yes | Yes
/invites/accept | POST | Invites | Accept invite (no auth) | No | Yes | Yes | Yes | Token validated; profile created on accept
/clients | GET | Clients | List clients | Yes | Yes | Yes | Yes
/clients | POST | Clients | Create client | Yes | Yes | Yes | Yes
/clients/{id} | GET | Clients | Client detail | Yes | Yes | Yes | Yes
/clients/{id} | PUT | Clients | Update client | Yes | Yes | Yes | Yes
/clients/{id} | DELETE | Clients | Delete client | Yes | Yes | Yes | Yes
/vendor/jobs | GET | Vendor | Vendor-visible jobs only | Yes | Yes | Yes | Yes | Vendor role enforced at API
/vendor/submissions | GET | Vendor | Vendor's own submissions | Yes | Yes | Yes | Yes | PIPE-005
/ai-interview-questions | POST | AI | Generate AI interview questions for role | Yes | Yes | Yes | Yes | AI-003; Celery background
/users | GET | Users | List org users | Yes | Yes | Yes | Yes
/me | GET | Auth | Current user profile + permissions | Yes | Yes | Yes | Yes
/health | GET | Infra | Health check endpoint | No | Yes | Yes | N/A
/docs | GET | Infra | Swagger UI | No | Yes | Yes | N/A | Auto-generated by FastAPI
/redoc | GET | Infra | ReDoc API docs | No | Yes | Yes | N/A | Auto-generated by FastAPI

## Infrastructure
Infrastructure Component | Status | Configured? | Production Ready? | Notes
FastAPI Backend | Completed | Yes | Yes | Python 3.11+; uvicorn ASGI server; modular router architecture; 25 route modules
PostgreSQL / Supabase | Completed | Yes | Yes | Supabase-hosted Postgres; SQLAlchemy ORM; 65+ Alembic migrations across full feature history
Alembic Migrations | Completed | Yes | Yes | 65+ migration files; merge heads managed for parallel branches; run alembic upgrade head for new envs
SQLAlchemy ORM | Completed | Yes | Yes | Declarative models; relationship-based queries; org-scoped via organization_id on all tables
Celery Task Queue | Completed | Partial | Partial | 6-queue topology: ai, email, notifications, integrations, background, deadletter; requires Redis; beat scheduler for reminders
Redis Broker | Configured | Partial | Partial | Used by Celery; CELERY_BROKER_URL env var required; not bundled with repo; must provision separately
JWT Authentication | Completed | Yes | Yes | HS256; access + refresh tokens; concurrent session limits; configurable expiry via env vars
RBAC Middleware | Completed | Yes | Yes | Permission-based route guards; org-scoped; 60+ permission constants; require_permission & require_any_permissions decorators
CORS | Completed | Yes | Partial | Origins list in CORS_ORIGINS env var; defaults to localhost; must update to production domain(s)
Brevo SMTP (Email) | Completed | Partial | Partial | Transactional email via Brevo SMTP relay; SMTP_HOST/USER/PASSWORD/FROM required in prod .env
OpenAI API | Completed | Partial | Partial | GPT-4o: resume parsing, screening questions, interview summary, copilot, JD normalization; OPENAI_API_KEY required
Grok / xAI API | Completed | Partial | Partial | grok-2-latest: semantic ATS enrichment; GROK_API_KEY + GROK_API_BASE in env; graceful fallback if missing
LiveKit | Completed | Partial | Partial | Video interview rooms; LIVEKIT_API_KEY + LIVEKIT_API_SECRET + LIVEKIT_WS_URL required; livekit-api SDK installed
AssemblyAI | Completed | Partial | Partial | Realtime transcription; ASSEMBLYAI_API_KEY required; WebSocket streaming from browser via short-lived session tokens
Whisper (OpenAI) | Completed | Partial | Partial | Audio transcription via whisper-1 model; available as fallback transcription provider; shares OPENAI_API_KEY
Swagger UI / OpenAPI | Completed | Yes | Yes | Auto-generated from FastAPI route definitions; available at /docs
ReDoc | Completed | Yes | Yes | Alternative OpenAPI UI at /redoc; auto-generated
Next.js Frontend | Completed | Yes | Yes | Next.js 14 App Router; TypeScript; Tailwind CSS; modular component architecture
Pydantic Settings | Completed | Yes | Yes | pydantic-settings v2; type-safe env config; AliasChoices for flexible env var naming
DLQ (Dead Letter Queue) | Completed | Partial | Partial | Celery deadletter queue defined; failed tasks routed for inspection; automated alerting not yet configured
Flower Worker Monitor | Configured | Partial | No | Celery Flower configured in celery_app; not deployed; available via celery flower --port=5555
Health Check Endpoint | Completed | Yes | Yes | GET /health returns service status; suitable for load balancer health checks
Error Handling | Completed | Yes | Yes | Structured HTTP exceptions; DLQ for async failures; tenacity retries (2 attempts) for all AI API calls
pg_trgm Extension | Completed | Yes | Yes | Full-text candidate search; trigram GIN index on candidates table; migration applied
Tenant Scoping | Completed | Yes | Yes | Organization_id enforced on all data queries; tested in test_tenant_scoping.py; no cross-org data leakage
Concurrent Session Limits | Completed | Yes | Yes | Per-org configurable max sessions; auth_sessions table with JWT hash tracking
Docker / Docker Compose | Pending | No | No | No Dockerfile or docker-compose.yml found in repository; deployment is currently manual
CI/CD Pipeline | Pending | No | No | No GitHub Actions or CI configuration found; manual deployment only; high risk for production
Rate Limiting | Pending | No | No | API rate limiting hooks exist in design but not implemented; Redis could be used for this
Environment Documentation | Partial | Partial | Partial | backend/.env.example exists with all required vars; missing deployment runbook and infrastructure docs

## Next Phase
Feature | Priority | Estimated Effort | Dependencies | Risk Level | Suggested Sprint | Notes
Docker Compose + Dockerfile | Critical | 1 week | Docker, hosting choice (Railway/Render/EC2) | High | Sprint 1 | Needed before any production deployment; blocking CI/CD
CI/CD Pipeline (GitHub Actions) | Critical | 2-3 days | Docker, secrets management | High | Sprint 1 | Automate test + build + deploy on PR merge
API Rate Limiting | High | 2-3 days | Redis (already in stack) | Medium | Sprint 1 | Protect AI endpoints from abuse; use Redis sliding window
Kanban Drag-and-Drop Pipeline Board | High | 3-5 days | React DnD or dnd-kit library | Medium | Sprint 1 | Current pipeline is table-only; Kanban is a UX priority
Google Calendar / MS Calendar Integration | High | 1 week | OAuth2 credentials; Google/Microsoft API | Medium | Sprint 2 | Auto-create calendar events on interview schedule
Naukri.com Sourcing Provider | High | 1 week | Naukri API credentials/partnership | Medium | Sprint 2 | Stub provider exists; needs real API integration
Automated Frontend Tests (Vitest/Playwright) | High | 1 week | Test environment setup | Medium | Sprint 2 | Currently no frontend test coverage; risk for regressions
Push Notifications (Web/Mobile) | Medium | 1 week | FCM / OneSignal / Pusher | Low | Sprint 2 | Currently email-only; web push notifications not implemented
Communication Hub UI (Full Inbox/Outbox) | Medium | 1 week | Backend tables complete; frontend only | Low | Sprint 2 | DB tables and email service done; hub page not complete
Bulk Candidate Import (CSV/Excel) | Medium | 3-5 days | Backend CSV parser, validation logic | Low | Sprint 2 | Manual candidate entry is slow for large import batches
Client Portal (External Client Login) | Medium | 2 weeks | New auth flow, separate role set for clients | High | Sprint 3 | Allows clients to log in and view their pipeline status
Settings Page (Org Configuration) | Medium | 3-5 days | Feature flags design, UX | Low | Sprint 3 | Currently a placeholder page; org config needed for prod
Pipeline Analytics — Advanced (Revenue, Source) | Medium | 1 week | Analytics data model extension | Medium | Sprint 3 | Add source-of-hire and revenue-per-placement analytics
ATS Score History / Trend Graph | Low | 2-3 days | Score history model (minor migration) | Low | Sprint 3 | Show how ATS score changed over time for a candidate
Interview Calendar View | Medium | 3-5 days | Calendar component (FullCalendar or similar) | Low | Sprint 4 | Current interview views are list-based; calendar view UX improvement
Slack / Teams Notification Integration | Low | 1 week | Slack/Teams OAuth, webhook setup | Low | Sprint 3 | Useful for real-time recruiter alerts on pipeline moves
Candidate Source Analytics | Low | 3-5 days | Source tagging on candidate import | Low | Sprint 3 | Track which sourcing channel produces best candidates
Role Analytics Dashboard | Low | 2-3 days |  | Low | Sprint 3 | Show permission usage and role distribution
Candidate Bulk Actions UI | Low | 3-5 days |  | Low | Sprint 4 | Select multiple candidates; bulk stage move, bulk delete
Mobile Responsive Polish | Medium | 1 week |  | Low | Sprint 4 | Workspace and pipeline views need mobile layout optimization
Flower Worker Dashboard (Deploy) | Medium | 1 day | Celery Flower (already configured) | Low | Sprint 1 | Already configured; just needs deployment + basic auth
Environment Runbook / Deploy Docs | High | 1-2 days |  | Medium | Sprint 1 | Document all required env vars, startup order, migration steps
Phase 2: Multi-org SaaS Billing | Low | 3-4 weeks | Stripe, subscription model design | High | Phase 2 | Full SaaS billing model; org subscription tiers; usage limits
Phase 2: Candidate Self-Service Portal | Low | 2-3 weeks | New auth flow, candidate-facing UI | High | Phase 2 | Allow candidates to track their own application status
Phase 2: Advanced AI Matching (Vector DB) | Low | 3-4 weeks | pgvector or Pinecone, embedding pipeline | High | Phase 2 | Replace keyword matching with dense vector similarity search